Aaliyah Vincent

PHC 6067

17. October 2025

Class Project Proposal (Updated)

Abstract

I will compare a Naive Bayes Bayesian Network (BN) with data-driven (learned) Bayesian networks for classifying lung tumor vs. matched normal samples from GEO GSE19804. All variables will be discretized (genes into Low/High or Low/Med/High; Stage). I will (i) estimate tabular CPDs, (ii) score and compare three structure hypotheses using log-likelihood/BIC, and (iii) evaluate predictive accuracy through a stratified, patient-wise 5-fold CV. I will also answer inference queries about likely gene-activity patterns and risk, linking conclusions to d-separation.

Introduction/Background

Lung cancer remains a leading cause of mortality in the United States. Essentially, gene-expression profiles can distinguish tumors from normal tissue. GSE19804 provides paired tumor/adjacent-normal microarray samples from non-smoking female patients, offering clear labels and balanced classes.

Question

- Can a simple Naive Bayes model perform as well as, or be outperformed by, a BN learned from the data for tumor/normal classification; Which conditional independencies are most supported by the data?

Significance

- Interpretable Bayesian Networks expose dependencies among clinical and molecular variables and provide probabilistic predictions.

Dataset

- GEO GSE19804: paired lung tumor and adjacent normal samples from non-smoking female patients (balanced labels and clear pairing).

Variables

- Y: Class (Tumor/Normal)

- Stage: Cancer Stage (I-IV)

- X_g: Discretized expression for 20-30 top variance genes

Goals/Hypotheses

- H1 (Naive Bayes): encodes

- H2 (Lightly Structured): adds sparse gene-gene/Stage-Y edges

- H3 (Learned BN): Obtained by score-based search under sparsity constraints

We hypothesize that H3 will achieve a higher BIC than H1 if the data support residual dependencies beyond Naive Bayes

Methods (Data Analysis)

Data Prep

- Build a patient-ID index (to keep pairs together). Within each training split: select top-variance genes, discretize by quantiles (2-3 bins), and apply the learned cutpoints to the test split. Model class. Discrete Bayesian Networks with tabular CPDs. The joint factorizes as:

Structure Hypotheses

- H1 (Naive Bayes): for all g; independence

- H2 (Lightly Structure): plus 1 peer parent per gene, including (direction chosen by score)

- H3 (Learned BN): Greedy hill climb with BIC, max in-degree 2, and a restricted candidate edge set. Parameter learning. Maximum-likelihood (counts) with Laplace smoothing.

- Log-likelihood:

- BIC:   (penalizes complexity)

- Model Comparison: Choose the hypothesis with highest BIC & report LL

Inferences (Queries)

- P(Y = Tumor | Stage, gene pattern)

- Most likely gene-activity combination for a subset S:

- Use d-separation to explain when genes become independent once conditioning on Y (Naive Bayes) versus learned structures.

Evaluation

- Protocol: Stratified 5-fold cross-validation with patient-wise grouping (keeping each patient’s tumor+normal in the same fold).

- Predictive metrics: Accuracy (), a pooled confusion matrix, & compare to a majority-class baseline

- Model comparison metrics: Report BIC and log-likelihood for H1-H3

- Baselines & sensitivity: Majority-class baseline, sensitivity to #genes (20 vs 30) and binning (2 vs 3 bins)

Timeline (dated weekly outcomes)

Week 1 (10/13-10/19) - Data & framing

- Download/inspect GSE 19804, build metadata (patient IDs, tumor/normal, stages).

- QC snapshot and normalization check, finalize variable list, and edge constraints.

Week 2 (10/20-10/26) - Feature pipeline set

- Implement fold-wise top variance selection (target 20-30 genes)

- Implement fold-wise discretization (2-3 bins) and lock the binning scheme.

Week 3 (10/27-11/2) - H1 Naive Bayes

- Train H1 (Naive Bayes) with Laplace smoothing

- Run stratified patient-wise 5 fold CV, record accuracy, and pooled confusion matrix

- Verify BN diagram, factorization, I-map, & parameter count

Week 4 (11/03-11/09) - H2 Light Structure

- Implement constrained search (TAN-style cap: 1 peer parent per gene, )

- Compute log-likelihood and BIC for H1 vs H2 & CV comparison

Week 5 (11/10-11/16) - H3 learned BN

- Greedy hill climb with BIC (max in-degree2, restricted edge set)

- Record LL/BIC & run CV accuracy

Week 6 (11/17-11/23) - Model comparison & inference

- Summarize H1-H3: LL, BIC, CV metrics

- Draft inference examples: P(Y = Tumor | Stage, gene pattern)

- Note d-separation insights (what becomes independent under each structure)

Week 7 (11/24-11/30) - Thanksgiving Buffer/Clean Up

- Light week: fix any data/metrics issues & finalize which model is “best” by BIC

- Start figures: structure diagrams, accuracy table, confusion matrix, LL/BIC table

Week 8 (12/01-12/07) - Writing Sprint

- Draft abstract, introduction/background, and methods for paper

- Insert all figures/tables, write results (H1-H3 comparison) and discussion

Week 9 (12/08-12/11) - Polish Checks

- Proofread, verify equations, & cross-check numbers

- Finalize references

Final Submission (12/12)

- Submit the class project paper and upload code/notebook as required

References

Koller, D., & Friedman, N. (2012). Probabilistic graphical models principles and techniques Daphne Koller; Nir Friedman. MIT Press.

T, L., L, L., & EY, C. (n.d.). Genome-wide screening of transcriptional modulation in non-smoking female lung cancer in Taiwan. National Center for Biotechnology Information. https://www.ncbi.nlm.nih.gov/geo/query/acc.cgi?acc=GSE19804